## Budget-Rehearsal Dinner
📌 BUDGET BREAKDOWN | CHRISTINE & BRADLEY'S |  | **This is not a quote** This is a sample estimate based on the total wedding budget, planner expertise & preferred vendors rates - Pricing above are not guaranteed!! budget breakdown above will be adjusted thourough the step by step process.
WEDDING
REHEARSAL DINNER | 65 | GUESTS
TYPE OF SERVICE | DESCRIPTION OF SERVICE | ESTIMATED PRICE | NOTES
VENUE | Venue + Food and Beverages | 15,000.00 € to 25,000.00 € | TBD
DECOR & FLOWERS | Floral decor | 0 | TBD
PHOTOGRAPHER | 2 hours | 0 | Depends on the photographer selected, combo deal may be done
VIDEOGRAPHER | 2 hours | 0 | Depends on the videographer selected, combo deal may be done
ENTERTAINMENT | DJ or Musicians | 0 | Depends on the DJ or musician selected, combo deal may be done
TOTAL |  | 15,000.00 € to 25,000.00 € | TO READ CAREFULLY: The current maximum allocation for the rehearsal dinner and the welcome party ranges between 15,000.00 € and 25,000.00 €, and for instance, it is not included in the overall wedding budget of 85,000.00 €. As agreed with the clients, the primary focus of the 85,000.00 € budget is the wedding day itself. Within this framework, we will strive to include as much as possible for the rehearsal dinner or welcome event; however, final pricing is subject to the discretion of the selected venues, restaurants, and vendors, as well as the number of guests. Therefore, either the dinner format may need to be adjusted to a cocktail-style or welcome dinner, or the number of guests may need to be significantly reduced to remain within budget. The level of customization requested will also impact final costs. Should the allocated budget remain unchanged, expectations and inclusions may need to be revised accordingly.

## Budget-Wedding Day
📌 BUDGET BREAKDOWN | CHRISTINE & BRADLEY'S |  | **This is not a quote** This is a sample estimate based on the total wedding budget, planner expertise & preferred vendors rates - Pricing above are not guaranteed!! budget breakdown above will be adjusted thourough the step by step process.
WEDDING
WEDDING DAY | 65 | GUESTS
TYPE OF SERVICE | DESCRIPTION OF SERVICE | ESTIMATED PRICE | NOTES
VENUE | Venue | 25000 | Depends on the venue selected. Some Château may include up to one night of accomadation.
CATERER | Food & beverage | 16800 | Catering (cocktail + dinner + beverage) starting at 220€/person. Custom menus & upgrades available. Estimated pricing based on our preferred vendors' deals.
CAKE DESIGNER | Wedding cake | 1500 | Depending on the design and Cake designer, if not included with the caterer selected.
BAR | Full Bar | TBD | A full mixology experience with an independent bartending company typically ranges between €6,000 and €11,500, depending on your guest count. Please note that certain premium items, such as specific liquors, champagne, or wine selections, are usually quoted separately. We also have the option to explore a more classic bar setup through the catering company, which can sometimes be more cost-effective. Our recommendation would be to first review the catering quotes we will be providing. Once those are assessed, we can then explore additional bar options if needed. This approach will allow us to make the most strategic and budget-conscious decision.
RENTALS | Rentals | 6000 | 4,000 € up to 12,000 € - Depending on the final design selected, this estimated price reflects the updated rentals and the upscale design. Some basic rentals may also be included with the chosen venue.
LIGHTING | Lighting design, ambient and colored illuminations, etc... | 3500 | Starting price for uplights, whether indoor or outdoor, will depend on the number of spaces to be illuminated. If the dinner changes to be outdoor, budget will have to be revised around 7,000€.
DECOR & FLOWERS | Floral decor | 15000 | Estimated Price – This will depend on the overall budget. However, please note that the amount mentioned is significantly below the average cost of wedding décor, which typically starts at a minimum of 12,000€ – 22,000€. We will review the possibilities together during the design phase, but transparency is essential on our end — this estimate may need to be adjusted or revised accordingly. TBD
STATIONERY | Printings | 950 | TBD - Not included in the budget. Depend on the budget: Wedding signs, menu, place cards etc…
VIDEOGRAPHER | 8 hours Videographer services | 4500 | Depends on Videographer selected (additional cost may apply for extra shooter or engagement session) - Better deal can be negotaited if photo/video is purchased as a combo wih the same team - TBD
PHOTOGRAPHER | 8 hours Photography services | 4500 | Depends on Photographer selected (additional cost may apply for extra shooter or engagement session) - Better deal can be negotaited if photo/video is purchased as a combo wih the same team - TBD
PHOTOBOOTH | 3 hours Photobooth services | TBD | Optional - TBD
CONTENT CREATOR | Content Creator for wedding day | TBD | Optional - Starting price 850€ depending on package selected - up to 3,000€.
HAIR & MAKEUP | Bride only | 950 | Bride + Trial average price ois 950 € / price will increase for additional guests around 2,500 € - + 2/3 guests depending on services requested for each guests.
OFFICIANT | For ceremony | 1200 | Bilingual Officiant.
MC | MC Services | 1200 | Billingual MC - Please refer to the MC section in the FAQ attached to this masterfile.
ENTERTAINMENT | Entertainment | TBD | Optional - Example: Fire works, Live Painter, Ballerinas , & other Performers. TBD - Starting price 2,500 € - 7,000 € .
MUSICIANS | Solo/Harpist/Violonist | TBD | Estimated price for a Solo for ceremony & cocktail - Depending on clients request and type of musicians/instruments selected.
DJ SERVICES | Dj Services | 4500 | Full DJ service & sound system for ceremony, cocktail, and reception/dancefloor.
LIVE BAND | Live Band | TBD | Live Band including 5/7 musicians + sound system, starting price: 10,000€
TRANSPORTATION | Bride/Groom car | TBD | Estimated price based on a car for Bride & Groom - Additional transportation for guests - Estimate of 2 buses 2,500 € ++.
TOTAL |  | 85600 | NOTE: Max Budget is 85,000.00€

## Budget-Brunch
📌 BUDGET BREAKDOWN | CHRISTINE & BRADLEY'S |  | **This is not a quote** This is a sample estimate based on the total wedding budget, planner expertise & preferred vendors rates - Pricing above are not guaranteed!! budget breakdown above will be adjusted thourough the step by step process.
WEDDING
GOODBYE BREAKFAST | 65 | GUESTS
TYPE OF SERVICE | DESCRIPTION OF SERVICE | ESTIMATED PRICE | NOTES
BRUNCH | Food & Beverage | 5,000.00 € to 10,000.00 € | Brunch/Breakfast – Depending on whether privatization is required.
PHOTOGRAPHER | 2 hours | 0 | Depends on the photographer selected, combo deal may be done
DECOR & FLOWERS | Floral decor | 0 | TBD
TOTAL |  | 5,000.00 € to 10,000.00 € | Note: Maximum budget is between 5,000.00 € and 10,000.00 €. This is not included in the main budget and depends on the type of brunch needed, but we can provide an estimate upon request.

## Deadlines
📌 DEADLINES | CHRISTINE & BRADLEY'S
WEDDING
| 65 | GUESTS
TYPE OF SERVICE | DEADLINES |  | NOTES | BOOKED | PENDING/CURRENT
VENUE | BOOKED
REHEARSAL DINNER | PENDING |  | Parents of the groom to make their final decision between both boat options
CATERER | BOOKED |  | Final selection to be made
BAR | PENDING |  | Final selection to be made
CAKE | Should be booked by April 25th, 2026 |  | - if external to Caterer selected -
PHOTOGRAPHER | BOOKED |  | Manda
VIDEOGRAPHER | PENDING
PHOTOBOOTH | Should be booked by May 17th, 2026 |  | - if applicable -
WEDDING OFFICIANT/MC SERVICES | Should be booked by June 1st, 2026
MUSICIANS/DJ | Should be booked by June 15th, 2026
HAIR & MAKEUP | Must be done by June 15th, 2026
ENTERTAINMENT | Should be booked by June 30th, 2026 |  | - if applicable -
TRANSPORTATION | Should be booked by July 15th, 2026 |  | - if applicable -
MOOD BOARD | Must be done by May 19th, 2026
DÉCOR/RENTALS/ LIGHTS & FLOWERS | Must be booked by June 26th, 2026
LAST DETAILS & POTENTIAL EXTRA REQUESTS | We will focus on last details between June 26th & July 31st, 2026 |  | - if applicable -
FINAL DEADLINE - Day of documents | Documents must be received by June 26th, 2026 |  | Day-Of docs will be provided by planner and must be received back - No later than 60 days prior to the wedding - Deadline will be adjusted depending on final wedding date.
SAVE THE DATES |  |  | Audrey's Note: I would suggest to skip the STD and sent the invites
INVITATIONS | Should be sent by March 25th, 2026 |  | 5 months prior to the wedding
RSVPs | Should be received back from guests by July 10th, 2026 |  | That gives about 5 months to your guests to answer - No later than 45 days prior to the wedding

## Payment Tracker
📌 PAYMENT TRACKER | CHRISTINE & BRADLEY'S
WEDDING
| 65 | GUESTS
SERVICE | VENDOR'S NAME | DEPOSIT | DEPOSIT DATE | BALANCE DUE | TOTAL PRICE | BALANCE DATE
VENUE |  | 0 |  | 0 | 0 | July 1st, 2026
CATERER |  | 0 |  | 0 | 0 | July 1st, 2026
CAKE DESIGNER |  | 0 |  | 0 | 0 | July 1st, 2026
WELCOME DINNER |  | 0 |  | 0 | 0 | July 1st, 2026
RENTALS |  | 0 |  | 0 | 0 | July 1st, 2026
LIGHTING |  | 0 |  | 0 | 0 | July 1st, 2026
DECOR & FLOWERS |  | 0 |  | 0 | 0 | July 1st, 2026
STATIONNARY |  | 0 |  | 0 | 0 | July 1st, 2026
VIDEOGRAPHER |  | 0 |  | 0 | 0 | July 1st, 2026
PHOTOGRAPHER |  | 0 |  | 0 | 0 | July 1st, 2026
CONTENT CREATOR |  | 0 |  | 0 | 0 | July 1st, 2026
HAIR & MAKEUP |  | 0 |  | 0 | 0 | July 1st, 2026
OFFICIANT |  | 0 |  | 0 | 0 | July 1st, 2026
MC |  | 0 |  | 0 | 0 | July 1st, 2026
ENTERTAINMENT |  | 0 |  | 0 | 0 | July 1st, 2026
MUSICIANS |  | 0 |  | 0 | 0 | July 1st, 2026
DJ SERVICES |  | 0 |  | 0 | 0 | July 1st, 2026
LIVE BAND |  | 0 |  | 0 | 0 | July 1st, 2026
TRANSPORTATION |  | 0 |  | 0 | 0 | July 1st, 2026
PLANNING | Dream Paris Wedding | 9450 | January 31st, 2026 | 0 | 9450 | January 31st, 2026
TOTAL |  |  |  |  | 9450

## Step-by-step Guide
📌 STEP BY STEP GUIDE | CHRISTINE & BRADLEY'S
WEDDING
| 65 | GUESTS

## FAQ
📌 FAQ | CHRISTINE & BRADLEY'S
WEDDING
| 65 | GUESTS | 1/6
2/6
3/6
4/6
5/6
6/6