DPCA — Week 5 Task Plan

────────────────────────────────────────────────────────────────────────────────

Date: 2026-05-04 (Monday)

Hard Deadline: Saturday 2026-05-09 — Gmail full workflow live end-to-end

Source docs: docs/SONNET_EXECUTION.md, docs/IMPLEMENTATION_PLAN.md

────────────────────────────────────────────────────────────────────────────────

AI PROVIDER DECISION

Claude AI (Anthropic) replaces OpenAI GPT-4o for all LLM tasks:

Classification (P2), draft generation (P1/P3/P5), lead extraction (P4), tone validation (P6)

Package: @anthropic-ai/sdk · Models: claude-sonnet-4-6 (classify/draft), claude-haiku-4-5-20251001 (tone validation)

Embeddings exception: Anthropic has no embeddings API. OpenAI text-embedding-3-small (1536-dim) is kept only for Pinecone vector embeddings. Alternatively, Voyage AI (voyage-3) can replace this in a future sprint but requires recreating the Pinecone index at 1024 dims.

ANTHROPIC_API_KEY added to .env.example. OPENAI_API_KEY remains for embeddings only.

────────────────────────────────────────────────────────────────────────────────

DEFINITION OF "GMAIL FULL WORKFLOW DONE"

A real email arrives at the DPW Gmail inbox → ingested → classified by Claude Sonnet → context retrieved from Pinecone → draft generated with correct sender persona, sanitizers passed → team approves via dashboard → reply sent back into the original Gmail thread with the correct subject, sender, and signature.

────────────────────────────────────────────────────────────────────────────────

WHAT IS ALREADY DONE

| Item | Status |
| --- | --- |
| DB schema (10 tables, 22 RLS, 7 triggers) | ✅ Done |
| Backend skeleton (routes, Zod, Supabase client) | ✅ Done |
| Dashboard skeleton (login, inbox 3-panel, leads, KB, settings) | ✅ Done |
| WF1 (Gmail polling, MIME decode, dedup, DB insert, label, WF2 trigger) | ✅ Working |
| n8n workflow JSONs WF2–WF8 (stubs only) | ✅ Skeleton only |
| .env.example, docker-compose.yml, project scaffolding | ✅ Done |

────────────────────────────────────────────────────────────────────────────────

ORDERED TASK LIST WITH TIMELINE

DAY 1 — Monday 2026-05-04 ✅ COMPLETE

Goal: Clean foundation — schema correct, DB seeded, backend secured

| # | Task | Status | What Was Done |
| --- | --- | --- | --- |
| 1 | Schema/code drift fixes | ✅ Done | drafts.ts: review_notes → rejection_reason (schema + handler). webhooks.ts: confidence_score → classification_confidence + added classification_reasoning; lead fields renamed (client_name→client_names[], client_email→email, client_phone→phone, source→source_channel); added location, wedding_date_flexible, how_found_us; errors_log.source → workflow_name. tsc --noEmit passes clean. |
| 2 | DB migrations + system_config seed | ✅ Done | 20260429000001_planning_step_and_signature.sql: adds planning_step, signature_signed, signed_at to leads; adds sender_persona, sender_email, subject_line, planning_step to drafts; creates planning_step_history table with RLS. 20260429000002_seed_brand_config.sql: seeds P1–P6 prompts, sender_routing, planning_step_subjects, forbidden_tokens, pre_signature_constraint, auto_send_rules. Run `supabase db push` to apply. |
| 3 | Backend auth + HMAC middleware | ✅ Done | Created backend/src/middleware/auth.ts (requireAuth, requireRole). Created backend/src/middleware/hmac.ts (requireHmac, requireInternalToken). Updated index.ts: requireAuth on messages/drafts/inboxes/leads; requireHmac on webhooks; /health stays open. |
| 4 | ⚠️ Manual: Rotate Supabase service-role JWT | ⚠️ YOU MUST DO | Go to Supabase dashboard → Settings → API → rotate the service-role key. The old key is committed in n8n-workflows/WF1-email-ingestion.json. Do NOT run WF6 until rotated. |

Remaining for today: Run supabase db push to apply the two migrations. Verify with SELECT config_key FROM system_config ORDER BY config_key; — expect 15+ rows.

────────────────────────────────────────────────────────────────────────────────

DAY 2 — Tuesday 2026-05-05

Goal: AI services implemented in backend using Claude Sonnet

| # | Task | Source Ref | Key Actions |
| --- | --- | --- | --- |
| 5 | AI service libs | SONNET Task 4 (part 1) | Install npm install @anthropic-ai/sdk in backend/ (replaces openai for LLM). Keep npm install openai for embeddings only. Create backend/src/lib/anthropic.ts (Anthropic client + model constants). Create backend/src/lib/openai.ts (OpenAI client for embeddings only — no chat completions). Create backend/src/lib/pinecone.ts (Pinecone client + index). Create backend/src/lib/systemConfig.ts (60s cached config getter). |
| 6 | Classifier service | SONNET Task 4 (part 2) | Create backend/src/services/classifier.ts: fetch message → render P2 prompt → call Claude Sonnet (messages.create, max_tokens: 300) with system: classification_prompt and user: rendered context → parse JSON → apply safety overrides → update messages row with classification_confidence. |
| 7 | Retrieval service | SONNET Task 4 (part 3) | Create backend/src/services/retrieval.ts: embed query via OpenAI text-embedding-3-small → Pinecone query with filter: { category: { $in: filterMap[category] } } → hydrate KB rows from Supabase → return { context_text, source_ids }. |
| 8 | Sanitizers | SONNET Task 4 (part 4) | Create backend/src/services/sanitizers.ts: commissionSanitize() (loads forbidden_tokens from config), callAvailabilitySanitize() (replaces non-Mon/Wed day offers), subjectLineEnforcer() (exact-match). |

────────────────────────────────────────────────────────────────────────────────

DAY 3 — Wednesday 2026-05-06

Goal: Draft generator + lead extractor + internal routes

| # | Task | Source Ref | Key Actions |
| --- | --- | --- | --- |
| 9 | Draft generator service | SONNET Task 4 (part 5) | Create backend/src/services/draftGenerator.ts: fetch message + lead → determine planning_step + signature_signed → look up sender persona + fixed subject from system_config → retrieve context → build system message from P1 (fill all slots) + user message from P3/P5 → call Claude Sonnet (max_tokens: 1024, temperature: 1 — Claude uses 0-1 temperature scale) → run commissionSanitize (2 retries then flag) → run callAvailabilitySanitize → call Claude Haiku for P6 tone validation → insert draft with all fields. |
| 10 | Lead extractor + embedder | SONNET Task 4 (part 6) | Create backend/src/services/leadExtractor.ts (Claude Sonnet with P4, upsert leads by email). Create backend/src/services/embedder.ts (OpenAI text-embedding-3-small, upsert to Pinecone, update embedding_status='embedded'). |
| 11 | Internal API routes | SONNET Task 4 (part 7) | Create backend/src/routes/internal.ts with requireInternalToken: POST /classify, POST /generate-draft, POST /extract-lead, POST /embed-kb, POST /retrieve, POST /dashboard-action. Mount at /api/internal in index.ts. |

────────────────────────────────────────────────────────────────────────────────

DAY 4 — Thursday 2026-05-07

Goal: Wire n8n workflows — make the Gmail pipeline actually run end-to-end

| # | Task | Source Ref | Key Actions |
| --- | --- | --- | --- |
| 12 | WF1 — remove hardcoded JWT | SONNET Task 5 | After rotating key (Day 1): replace inline JWT in n8n-workflows/WF1-email-ingestion.json with n8n credential node reference (Supabase REST - Service Role, type: Header Auth). Re-import into n8n and verify. |
| 13 | WF2 — thin HTTP orchestrator | SONNET Task 5 | Rebuild n8n-workflows/WF2-classification.json: webhook trigger → HTTP call POST /api/internal/classify (with x-internal-token header) → decision node: if tier===3 notify branch, else trigger WF5; if new_inquiry also trigger WF7. |
| 14 | WF5 — thin HTTP orchestrator | SONNET Task 5 | Rebuild n8n-workflows/WF5-draft-generation.json: webhook → HTTP call POST /api/internal/generate-draft → if auto_send: true trigger WF6, else end (draft awaits review). |
| 15 | WF6 — Gmail send (CRITICAL) | SONNET Task 5 | Rebuild n8n-workflows/WF6-auto-send.json: webhook → fetch draft+message via /api/internal/messages/:id → Gmail Send node (from: draft.sender_email, subject: draft.subject_line, body: draft.draft_text, In-Reply-To + thread, CC if present) → apply label AI-Sent, remove AI-Processing → 3 retries with exponential backoff → HTTP callback POST /api/webhooks/n8n/send-result with HMAC signature. WhatsApp/Instagram: stub send_failed. |
| 16 | WF7 + WF8 | SONNET Task 5 | WF7: webhook → POST /api/internal/extract-lead. WF8: webhook → POST /api/internal/dashboard-action. |

────────────────────────────────────────────────────────────────────────────────

DAY 5 — Friday 2026-05-08

Goal: Dashboard UX wired + KB seeded + smoke test

| # | Task | Source Ref | Key Actions |
| --- | --- | --- | --- |
| 17 | Dashboard auth fix | IMPL-PLAN 2.5 | Update all BACKEND_URL fetch calls in dashboard/app/inbox/page.tsx to include Authorization: Bearer ${session.access_token}. |
| 18 | Regenerate + Reject modals | SONNET Task 6 | Create dashboard/components/RegenerateModal.tsx and RejectModal.tsx. Wire into inbox/page.tsx. |
| 19 | KB import pipeline + seed | SONNET Task 7 | Create scripts/kb-import.ts. Create 15+ KB markdown files. Run script → verify embedding_status='embedded' on all via OpenAI embeddings. |
| 20 | End-to-end smoke test | SONNET Task 10 | Send real test email → verify within 90s: ingested → classified by Claude → draft generated with correct persona → approve in dashboard → reply sent in Gmail thread with AI-Sent label. |

────────────────────────────────────────────────────────────────────────────────

DAY 6 — Saturday 2026-05-09

Goal: Buffer, fixes, UAT

| # | Task | Notes |
| --- | --- | --- |
| 21 | Fix bugs from smoke test | Common points: OAuth token expiry, Pinecone empty results (check 1536 dim + string metadata), dashboard auth header, JWT not rotated. |
| 22 | Security checklist | No Supabase JWT in committed files; service_role not in dashboard code; HMAC on all webhooks; JWT on all backend routes. |
| 23 | Gmail workflow UAT | 3 scenarios: (a) new inquiry from unknown sender, (b) vendor communication, (c) general question. Verify tier, sender persona, draft quality. |

────────────────────────────────────────────────────────────────────────────────

PRIORITY ORDER SUMMARY

Day 1 ✅:  Task 1 (drift) → Task 2 (migrations+seed) → Task 3 (auth) → ⚠️ Rotate JWT (manual)
Day 2:     Task 5-libs(Anthropic+OpenAI) → Task 6-classifier(Claude) → Task 7-retrieval(OpenAI embed) → Task 8-sanitizers
Day 3:     Task 9-draftGenerator(Claude) → Task 10-leadExtractor+embedder → Task 11-internal routes
Day 4:     Task 12-WF1 fix → Task 13-WF2 → Task 14-WF5 → Task 15-WF6 Gmail → Task 16-WF7/8
Day 5:     Task 17-dashboard auth → Task 18-modals → Task 19-KB pipeline → Task 20-smoke test
Day 6:     Fix bugs → Security check → UAT

────────────────────────────────────────────────────────────────────────────────

BLOCKED / DEFERRED ITEMS (DO NOT WORK ON THESE THIS WEEK)

| Item | Blocked On | When |
| --- | --- | --- |
| WhatsApp send | Meta App Review | After Meta approval |
| Instagram send | Meta App Review | After Meta approval |
| Voyage AI embeddings (replace OpenAI) | Optional migration | Future sprint if desired |
| Audit log viewer page (Task 8) | Not blocking Gmail workflow | Week 6 |
| Analytics page (Task 8) | Not blocking Gmail workflow | Week 6 |
| Bulk inbox actions (Task 9) | Not blocking Gmail workflow | Week 6 |
| 150+ KB entries | Sophie/Audrey content delivery | Ongoing |

────────────────────────────────────────────────────────────────────────────────

CRITICAL RISKS THIS WEEK

| Risk | Mitigation |
| --- | --- |
| Supabase service-role JWT in WF1 git history | Rotate key on Day 1 BEFORE touching n8n. Do not run WF6 until done. |
| Claude API rate limits | claude-sonnet-4-6 has generous limits. Use claude-haiku-4-5-20251001 for tone validation to reduce cost/latency. |
| Pinecone empty results | Confirm index dimension = 1536 (matches text-embedding-3-small), category metadata stored as string, filter uses $in operator. |
| Claude returns non-JSON for classification/extraction | Use a JSON-enforcing system prompt suffix: "Return ONLY valid JSON, no preamble, no markdown fences." Retry once if parse fails. |
| Dashboard 401 after auth middleware added | Update every fetch(BACKEND_URL + ...) in dashboard to send Authorization: Bearer <session.access_token>. |
| Gmail OAuth token expired | Test token with a simple list-emails call before running the full pipeline. Reauthorize in n8n if needed. |